## OPTPortalProject
Task | Team | Priority | Owner | Status | Start date | End date | Milestone | Deliverable | Notes
How to join code to RDS Instance | Frontend Team | P0 | Rajas Telang | Completed | 2024-10-09 | 2024-10-11 | Took a meeting with Rajas and Saurav to clear RDS instance | OPT Portal Project Week 5 Deliverable_.pdf | Done
New Screens: Work sheet | Frontend Team | P1 | Rajas Telang | Completed | 2024-10-09 | 2024-10-11 | Brainstorm ideas for Timesheet section | OPT Portal Project Week 5 Deliverable_.pdf | Started working on Work sheet, Work Done: Page, form, remaning: Integration with database and populating it database; UI is done for the work sheet. Rajas will connect with Rolwyn,
Connected the flow of Figma, we have combined , protyping is left | UI/UX Team | P1 | Vishrutha Abbaiah | Completed | 2024-10-09 | 2024-10-11 | Helped Vishrutha with Integration | OPT Portal Project Week 5 Deliverable_.pdf | Done
Will help frontend with RDS Instance | Backend Team | P1 | Saurav Shaw | Completed | 2024-10-09 | 2024-10-11 | Helped Rajas with RDS | OPT Portal Project Week 5 Deliverable_.pdf | Done
Connecting frontend with progress sheet is difficult, hence brainstorming some ideas for it | Backend Team | P0 | Saurav Shaw | Completed | 2024-10-14 | 2024-10-18 | Roughly 45% of work done | OPT Portal Project Week 6 Deliverable.pdf | Today will be working on it
Assisting Rolwyn and helping him Onboarding | Frontend Team | P0 | Rajas Telang | Completed | 2024-10-14 | 2024-10-18 | Gave Rolwyn github and Figma access | OPT Portal Project Week 6 Deliverable.pdf | Done
Still have to go through the code and will be working on Timesheet | Frontend Team | P3 | Rolwyn Quadras | Completed | 2024-10-14 | 2024-10-18 | Gayathri suggested a functionality | OPT Portal Project Week 6 Deliverable.pdf | Work done: The UI Part and Design, Only the user part is done, admin part is left. After that Integration part will be done; Timeline- Atleast 2 weeks more. Need of role based authorization.
Notifications if you work less than 20 hours and also number of warnings, 3 warning or more they will be deleted from systems | Frontend Team | P3 | Rajas Telang | Completed | 2024-10-14 | 2024-10-18 | Brianstorming more ideas for funtionatility | OPT Portal Project Week 6 Deliverable.pdf
Admin Profile page work desigining | Frontend Team | P1 | Vishrutha Abbaiah | Completed | 2024-10-14 | 2024-10-18 | Discussed this admin page functionality in today's meeting | OPT Portal Project Week 6 Deliverable.pdf | Done
Progress sheet Structure view and classes are done. | Backend Team | P1 | Saurav Shaw | Completed | 2024-10-14 | 2024-10-18 | Saurav updates this | OPT Portal Project Week 6 Deliverable.pdf | Done
Health Monitoring and Kanban Integration | Backend Team | P3 | Hrithik Bandaru | Completed | 2024-10-14 | 2024-10-18 | Not attended today's meeting | OPT Portal Project Week 6 Deliverable.pdf
API Optimization and Work Tracker Sync | Backend Team | P0 | Saurav Shaw | Completed | 2024-10-14 | 2024-10-18 | Saurav will update us on this by monday | OPT Portal Project Week 6 Deliverable.pdf | Till now whatever needed is connected
Bug Fixing and Time Entry Integration | Backend Team | P1 | Saurav Shaw | Completed | 2024-10-18 | 2024-10-18 | Saurav will update us on this by monday | OPT Portal Project Week 6 Deliverable.pdf | Work in progress: Today
Security Audit and Logging Enhancements | Backend Team | P1 | Hrithik Bandaru | Completed | 2024-10-14 | 2024-10-18 | Not attended today's meeting | OPT Portal Project Week 6 Deliverable.pdf
Final Backend Review and Documentation | Backend Team | P2 | Saurav Shaw | Blocked | 2024-10-14 | 2024-10-18 | Will do it next week | OPT Portal Project Week 6 Deliverable.pdf
Kanban Integration and Performance Monitoring | Frontend Team | P1 | Rajas Telang | Completed | 2024-10-14 | 2024-10-18 | Rajas is working on this needs more time | OPT Portal Project Week 6 Deliverable.pdf | Tomorrow meeting with Manan
Work Tracker UI and Lazy Loading | Frontend Team | P3 | Rajas Telang | Blocked | 2024-10-14 | 2024-10-18 | Will do it next week | OPT Portal Project Week 6 Deliverable.pdf
Bug Fixing and Cross-Browser Testing | Frontend Team | P1 | Rajas Telang | Completed | 2024-10-14 | 2024-10-18 | Rajas is working on this needs more time | OPT Portal Project Week 6 Deliverable.pdf
Front-End Security and Kanban Updates | Frontend Team | P3 | Rolwyn Quadras | Completed | 2024-10-14 | 2024-10-18 | Rolwyn will start working on this next week | OPT Portal Project Week 6 Deliverable.pdf
Kanban and Work Tracker UX Review | UI/UX Team | P2 | Vishrutha Abbaiah | Completed | 2024-10-14 | 2024-10-18 | Vishrutha is working on this | OPT Portal Project Week 6 Deliverable.pdf | Navigation needs to be improved,
UI Bug Fixing and Feedback Integration | UI/UX Team | P2 | Vishrutha Abbaiah | Completed | 2024-10-14 | 2024-10-18 | Vishrutha is modified few designs | OPT Portal Project Week 6 Deliverable.pdf | Done
Help page for OPT portal | UI/UX Team | P1 | Vishrutha Abbaiah | Completed | 2024-10-21 | 2024-10-25 | Gayathri will share the content | OPT Portal Project Week 7 Deliverables.pdf | Help page will be done by the end of the week
Working on Design: Prodile page Title | UI/UX Team | P2 | Vishrutha Abbaiah | Completed | 2024-10-21 | 2024-10-25 | Vishrutha will collec | OPT Portal Project Week 7 Deliverables.pdf
Active and Inactive part for Volunteers and PM | Backend Team | P0 | Saurav Shaw | Completed | 2024-10-21 | 2024-10-25 | Volunteer left will go to inactive list and if they come back we will move them to active list(WIll do it in. Phase) | OPT Portal Project Week 7 Deliverables.pdf
Database Optimization and API Load Balancing | Backend Team | P2 | Saurav Shaw | Completed | 2024-10-21 | 2024-10-25 |  | OPT Portal Project Week 7 Deliverables.pdf
Work Tracker Enhancements and Error Handling | Backend Team | P2 | Saurav Shaw | Completed | 2024-10-21 | 2024-10-25 |  | OPT Portal Project Week 7 Deliverables.pdf | Will connect you with Natarajan
Role-based Access Control (RBAC) Enhancements | Backend Team | P3 | Saurav Shaw | Completed | 2024-10-21 | 2024-10-25 |  | OPT Portal Project Week 7 Deliverables.pdf
System Health and Logging Review | Backend Team | P3 | Saurav Shaw | Completed | 2024-10-21 | 2024-10-25 |  | OPT Portal Project Week 7 Deliverables.pdf
UI Optimization and Data Visualization Enhancements | Frontend Team | P1 | Rajas Telang | Completed | 2024-10-21 | 2024-10-25 |  | OPT Portal Project Week 7 Deliverables.pdf
Kanban Board Synchronization and Fixes | Frontend Team | P1 | Rajas Telang | Completed | 2024-10-21 | 2024-10-25 |  | OPT Portal Project Week 7 Deliverables.pdf
Session Management and Security Testing | Frontend Team | P2 | Rajas Telang | Completed | 2024-10-21 | 2024-10-25 |  | OPT Portal Project Week 7 Deliverables.pdf
Frontend Usability Testing and Bug Fixes | Frontend Team | P2 | Rolwyn Quadras | Completed | 2024-10-21 | 2024-10-25 |  | OPT Portal Project Week 7 Deliverables.pdf
Documentation and Deployment Readiness | Frontend Team | P1 | Rolwyn Quadras | Completed | 2024-10-21 | 2024-10-25 |  | OPT Portal Project Week 7 Deliverables.pdf
Design Review and Accessibility Improvements | UI/UX Team | P2 | Vishrutha Abbaiah | Completed | 2024-10-21 | 2024-10-25 |  | OPT Portal Project Week 7 Deliverables.pdf
Mobile UI Refinements and Error Messaging Improvements | UI/UX Team | P2 | Vishrutha Abbaiah | Completed | 2024-10-21 | 2024-10-25 |  | OPT Portal Project Week 7 Deliverables.pdf
Prototype Testing and User Walkthroughs | UI/UX Team | P3 | Vishrutha Abbaiah | Completed | 2024-10-21 | 2024-10-25 |  | OPT Portal Project Week 7 Deliverables.pdf
Email Notification Error | Frontend Team | P2 | Rajas Telang | Completed | 2024-10-25 | 2024-10-25 | Rajas will fix it today | OPT Portal Project Week 7 Deliverables.pdf | 2FA needs to be step up. $52 charge, May be the RDS instance, Once we can login and check. Will wait for the SS from professor
Timesheet Workflow Finalization and Escalation Logic | Backend Team | P0 | Saurav Shaw | Completed | 2024-10-28 | 2024-11-01 | Absent | OPT Portal Project Week 8 Deliverables.pdf
Approval and Email Notification System Enhancements | Backend Team | P2 | Saurav Shaw | Completed | 2024-10-28 | 2024-11-01 | Absent | OPT Portal Project Week 8 Deliverables.pdf
Security and Audit Trail Review | Backend Team | P1 | Saurav Shaw | Blocked | 2024-10-28 | 2024-11-01 | Absent | OPT Portal Project Week 8 Deliverables.pdf
Reporting and Analytics Integration | Backend Team | P3 | Saurav Shaw | Completed | 2024-10-28 | 2024-11-01 | Absent | OPT Portal Project Week 8 Deliverables.pdf
Final Backend Review and Documentation | Backend Team | P0 | Saurav Shaw | Completed | 2024-10-28 | 2024-11-01 | Absent | OPT Portal Project Week 8 Deliverables.pdf
Dashboard Enhancements and Usability Testing | Frontend Team | P1 | Rajas Telang | Completed | 2024-10-28 | 2024-11-01 |  | OPT Portal Project Week 8 Deliverables.pdf
UI and Timesheet Entry Validation Improvements | Frontend Team | P2 | Rolwyn Quadras | Completed | 2024-10-28 | 2024-11-01 |  | OPT Portal Project Week 8 Deliverables.pdf
Email Notification UI and Real-Time Updates | Frontend Team | P3 | Rajas Telang | Completed | 2024-10-28 | 2024-11-01 |  | OPT Portal Project Week 8 Deliverables.pdf
Final Testing and Cross-Component Synchronization | Frontend Team | P0 | Rajas Telang | Completed | 2024-10-28 | 2024-11-01 |  | OPT Portal Project Week 8 Deliverables.pdf
Deployment Preparation and User Guides | Frontend Team | P3 | Rajas Telang | Completed | 2024-10-28 | 2024-11-01 |  | OPT Portal Project Week 8 Deliverables.pdf
Design Review and Accessibility Testing | UI/UX Team | P1 | Vishrutha Abbaiah | Completed | 2024-10-28 | 2024-11-01 |  | OPT Portal Project Week 8 Deliverables.pdf
Feedback Integration and Visual Cues | UI/UX Team | P0 | Vishrutha Abbaiah | Completed | 2024-10-28 | 2024-11-01 |  | OPT Portal Project Week 8 Deliverables.pdf
Prototype Testing and Documentation | UI/UX Team | P2 | Vishrutha Abbaiah | Completed | 2024-10-28 | 2024-11-01 |  | OPT Portal Project Week 8 Deliverables.pdf
Mobile Usability and Error Messaging Review | UI/UX Team | P2 | Vishrutha Abbaiah | Completed | 2024-10-28 | 2024-11-01 |  | OPT Portal Project Week 8 Deliverables.pdf
Final Review and Launch Readiness | UI/UX Team | P3 | Vishrutha Abbaiah | Completed | 2024-10-28 | 2024-11-01 |  | OPT Portal Project Week 8 Deliverables.pdf
Initial Post-Launch Monitoring and Issue Resolution | Backend Team | P0 | Saurav Shaw | Completed | 2024-11-04 | 2024-11-08 | Absent | OPT Portal Project Week 9 Deliverables.pdf
Security and Data Validation Check | Backend Team | P1 | Saurav Shaw | In progress | 2024-11-04 | 2024-11-08 |  | OPT Portal Project Week 9 Deliverables.pdf
Timesheet Module Enhancement Planning | Backend Team | P1 | Saurav Shaw | Blocked | 2024-11-04 | 2024-11-08 |  | OPT Portal Project Week 9 Deliverables.pdf
Reporting Refinements and Analytics Adjustment | Backend Team | P2 | Saurav Shaw | In progress | 2024-11-04 | 2024-11-08 |  | OPT Portal Project Week 9 Deliverables.pdf
Retrospective Documentation and Next Phase Planning | Backend Team | P3 | Saurav Shaw | In progress | 2024-11-04 | 2024-11-08 |  | OPT Portal Project Week 9 Deliverables.pdf
Initial Issue Resolution and User Feedback Collection | Frontend Team | P2 | Rajas Telang | Completed | 2024-11-04 | 2024-11-08 | Absent | OPT Portal Project Week 9 Deliverables.pdf
User Interface Fine-Tuning | Frontend Team | P0 | Rajas Telang | Completed | 2024-11-04 | 2024-11-08 |  | OPT Portal Project Week 9 Deliverables.pdf
Enhanced Mobile and Accessibility Testing | Frontend Team | P2 | Rolwyn Quadras | In progress | 2024-11-04 | 2024-11-08 | Absent | OPT Portal Project Week 9 Deliverables.pdf
Report and Dashboard Optimization | Frontend Team | P3 | Rolwyn Quadras | Completed | 2024-11-04 | 2024-11-08 |  | OPT Portal Project Week 9 Deliverables.pdf
Deployment Review and Code Documentation | Frontend Team | P1 | Rajas Telang | Completed | 2024-11-04 | 2024-11-08 |  | OPT Portal Project Week 9 Deliverables.pdf
Post-Launch User Experience Evaluation | UI/UX Team | P1 | Vishrutha Abbaiah | Completed | 2024-11-04 | 2024-11-08 | Absent | OPT Portal Project Week 9 Deliverables.pdf
Design Adjustments Based on Feedback | UI/UX Team | P0 | Vishrutha Abbaiah | Completed | 2024-11-04 | 2024-11-08 |  | OPT Portal Project Week 9 Deliverables.pdf
Error Messaging and Visual Cue Refinement | UI/UX Team | P3 | Vishrutha Abbaiah | Completed | 2024-11-04 | 2024-11-08 |  | OPT Portal Project Week 9 Deliverables.pdf
Accessibility Audit and Future Improvements | UI/UX Team | P1 | Vishrutha Abbaiah | Completed | 2024-11-04 | 2024-11-08 |  | OPT Portal Project Week 9 Deliverables.pdf
Post-Launch Retrospective and Documentation | UI/UX Team | P3 | Vishrutha Abbaiah | Completed | 2024-11-04 | 2024-11-08 |  | OPT Portal Project Week 9 Deliverables.pdf
No working software seen, Rajas and Rolwyn will update tomorrow | Frontend Team | P1 | Rajas Telang | In progress | 2024-11-11 | 2024-11-15 |  | OPT Portal Project Week 10 Deliverables.pdf
Time Sheet Bug Resolving | Frontend Team | P1 | Rolwyn Quadras | Completed | 2024-11-18 | 2024-11-22 | Time sheet and then will start working on it Search functionality | OPT Portal Project Week 11 Deliverables.pdf
Role based Authentication | Frontend Team | P1 | Rajas Telang | Completed | 2024-11-18 | 2024-11-22 | Rajas and Priyanak will be working from Monday | OPT Portal Project Week 11 Deliverables.pdf
Post-Launch Monitoring and Issue Resolution | Backend Team | P0 | Rajas Telang | In progress | 2024-11-18 | 2024-11-22 |  | OPT Portal Project Week 11 Deliverables.pdf
Feature Integration and Role Management Setup | Backend Team | P1 | Rajas Telang | Completed | 2024-11-18 | 2024-11-22 |  | OPT Portal Project Week 11 Deliverables.pdf
Database and API Enhancements | Backend Team | P2 | Rajas Telang | In progress | 2024-11-18 | 2024-11-22 |  | OPT Portal Project Week 11 Deliverables.pdf
Timesheet and Application Workflow Enhancements | Backend Team | P1 | Rajas Telang | In progress | 2024-11-18 | 2024-11-22 |  | OPT Portal Project Week 11 Deliverables.pdf
Retrospective, Documentation, and Knowledge Sharing | Backend Team | P0 | Rajas Telang | Completed | 2024-11-18 | 2024-11-22 |  | OPT Portal Project Week 11 Deliverables.pdf
Immediate Bug Fixes and UI Enhancements | Frontend Team | P0 | Rolwyn Quadras | Completed | 2024-11-18 | 2024-11-22 |  | OPT Portal Project Week 11 Deliverables.pdf
Role Management UI and Quick Wins | Frontend Team | P1 | Rolwyn Quadras | Completed | 2024-11-18 | 2024-11-22 |  | OPT Portal Project Week 11 Deliverables.pdf
Dashboard and Reporting Enhancements | Frontend Team | P2 | Rolwyn Quadras | In progress | 2024-11-18 | 2024-11-22 |  | OPT Portal Project Week 11 Deliverables.pdf
Documentation and Knowledge Transfer | Frontend Team | P2 | Rolwyn Quadras | In progress | 2024-11-18 | 2024-11-22 |  | OPT Portal Project Week 11 Deliverables.pdf
User Experience Analysis and Feedback | UI/UX Team | P0 | Vishrutha Abbaiah | Completed | 2024-11-18 | 2024-11-22 |  | OPT Portal Project Week 11 Deliverables.pdf
Accessibility and Visual Enhancements | UI/UX Team | P1 | Vishrutha Abbaiah | In progress | 2024-11-18 | 2024-11-22 |  | OPT Portal Project Week 11 Deliverables.pdf
Onboarding and Marketing Support | UI/UX Team | P1 | Vishrutha Abbaiah | Blocked | 2024-11-18 | 2024-11-22 |  | OPT Portal Project Week 11 Deliverables.pdf
Future Feature Prototyping | UI/UX Team | P3 | Vishrutha Abbaiah | In progress | 2024-11-18 | 2024-11-22 |  | OPT Portal Project Week 11 Deliverables.pdf
Retrospective and Knowledge Sharing | UI/UX Team | P2 | Vishrutha Abbaiah | In progress | 2024-11-18 | 2024-11-22 |  | OPT Portal Project Week 11 Deliverables.pdf
Phase 2 OPT Portal recording | Frontend Team | P0 | Rolwyn Quadras | Completed | 2024-11-18 | 2024-11-22 |  | OPT Portal Project Week 11 Deliverables.pdf
Approval Page | Frontend Team | P1 | Rolwyn Quadras | Completed | 2024-11-18 | 2024-11-22 |  | OPT Portal Project Week 11 Deliverables.pdf
Phase 3 Foundation Setup | Backend Team | P2 | Rajas Telang | In progress | 2024-11-25 | 2024-11-29 |  | OPT Portal Project Week 12 Deliverables.pdf
Volunteer Role Enhancements | Backend Team | P1 | Rajas Telang | In progress | 2024-11-25 | 2024-11-29 |  | OPT Portal Project Week 12 Deliverables.pdf
System Performance Enhancements | Backend Team | P3 | Rajas Telang | In progress | 2024-11-25 | 2024-11-29 |  | OPT Portal Project Week 12 Deliverables.pdf
Feature Testing and Data Integrity Checks | Frontend Team | P2 | Rolwyn Quadras | Completed | 2024-11-25 | 2024-11-29 |  | OPT Portal Project Week 12 Deliverables.pdf
Documentation and Knowledge Transfer | Frontend Team | P0 | Rolwyn Quadras | Completed | 2024-11-25 | 2024-11-29 |  | OPT Portal Project Week 12 Deliverables.pdf
New Feature Prototypes and Bug Fixes | Frontend Team | P1 | Rolwyn Quadras | In progress | 2024-11-25 | 2024-11-29 |  | OPT Portal Project Week 12 Deliverables.pdf
Role Management UI Enhancements | Frontend Team | P3 | Rolwyn Quadras | Completed | 2024-11-25 | 2024-11-29 |  | OPT Portal Project Week 12 Deliverables.pdf
UI Performance Optimization | Frontend Team | P2 | Rolwyn Quadras | Completed | 2024-11-25 | 2024-11-29 |  | OPT Portal Project Week 12 Deliverables.pdf
Integration Testing and Sync Validation | Frontend Team | P2 | Rolwyn Quadras | In progress | 2024-11-25 | 2024-11-29 |  | OPT Portal Project Week 12 Deliverables.pdf
Documentation and Planning | Frontend Team | P1 | Rolwyn Quadras | Blocked | 2024-11-25 | 2024-11-29 |  | OPT Portal Project Week 12 Deliverables.pdf
Phase 3 Initial Designs | UI/UX Team | P2 | Vishrutha Abbaiah | In progress | 2024-11-25 | 2024-11-29 |  | OPT Portal Project Week 12 Deliverables.pdf
Accessibility and Compliance Audits | UI/UX Team | P3 | Vishrutha Abbaiah | In progress | 2024-11-25 | 2024-11-29 |  | OPT Portal Project Week 12 Deliverables.pdf
Design Testing and Feedback | UI/UX Team | P0 | Vishrutha Abbaiah | In progress | 2024-11-25 | 2024-11-29 |  | OPT Portal Project Week 12 Deliverables.pdf
Visual Enhancements and Assets | UI/UX Team | P2 | Vishrutha Abbaiah | In progress | 2024-11-25 | 2024-11-29 |  | OPT Portal Project Week 12 Deliverables.pdf
Retrospective and Ideation | UI/UX Team | P0 | Vishrutha Abbaiah | Completed | 2024-11-25 | 2024-11-29 |  | OPT Portal Project Week 12 Deliverables.pdf
API Development and Optimization | Backend Team | P1 | Rajas Telang | In progress | 2024-12-02 | 2024-12-06 |  | OPT Portal Project Week 13 Deliverables.pdf
Database and Caching Enhancements | Backend Team | P2 | Rajas Telang | Completed | 2024-12-02 | 2024-12-06 |  | OPT Portal Project Week 13 Deliverables.pdf
Security and Validation | Backend Team | P3 | Rajas Telang | Completed | 2024-12-02 | 2024-12-06 |  | OPT Portal Project Week 13 Deliverables.pdf
Feature Integration Testing | Backend Team | P0 | Rajas Telang | In progress | 2024-12-02 | 2024-12-06 |  | OPT Portal Project Week 13 Deliverables.pdf
Documentation and Handoff | Backend Team | P2 | Rajas Telang | In progress | 2024-12-02 | 2024-12-06 |  | OPT Portal Project Week 13 Deliverables.pdf
UI Development for Software Tour | Frontend Team | P2 | Rolwyn Quadras | Completed | 2024-12-02 | 2024-12-06 | Role UI | OPT Portal Project Week 13 Deliverables.pdf
Enhanced Role Management UI | Frontend Team | P3 | Rolwyn Quadras | Completed | 2024-12-02 | 2024-12-06 | Timesheet validation and comment section is left, | OPT Portal Project Week 13 Deliverables.pdf
Performance Optimization | Frontend Team | P0 | Rolwyn Quadras | In progress | 2024-12-02 | 2024-12-06 |  | OPT Portal Project Week 13 Deliverables.pdf
Testing and Bug Fixes | Frontend Team | P1 | Rolwyn Quadras | Completed | 2024-12-02 | 2024-12-06 |  | OPT Portal Project Week 13 Deliverables.pdf
Documentation and Planning | Frontend Team | P2 | Rolwyn Quadras | In progress | 2024-12-02 | 2024-12-06 |  | OPT Portal Project Week 13 Deliverables.pdf
Finalize Onboarding Designs | UI/UX Team | P2 | Vishrutha Abbaiah | Completed | 2024-12-02 | 2024-12-06 | Virshutha has shared the design to Rolwyn on slack | OPT Portal Project Week 13 Deliverables.pdf
Accessibility and Usability Audits | UI/UX Team | P1 | Vishrutha Abbaiah | Not started | 2024-12-02 | 2024-12-06 |  | OPT Portal Project Week 13 Deliverables.pdf
Design Testing and Feedback | UI/UX Team | P1 | Vishrutha Abbaiah | In progress | 2024-12-02 | 2024-12-06 |  | OPT Portal Project Week 13 Deliverables.pdf
Visual Asset Creation | UI/UX Team | P2 | Vishrutha Abbaiah | In progress | 2024-12-02 | 2024-12-06 |  | OPT Portal Project Week 13 Deliverables.pdf
Retrospective and Ideation | UI/UX Team | P2 | Vishrutha Abbaiah | Blocked | 2024-12-02 | 2024-12-06 |  | OPT Portal Project Week 13 Deliverables.pdf
Intergration of the list of Voluteering | UI/UX Team | P2 | Vishrutha Abbaiah | In progress | 2024-12-09 | 2024-12-13 |  | OPT Portal Project Week 14 Deliverables.pdf
Protype of Different Roles | UI/UX Team | P2 | Vishrutha Abbaiah | In progress | 2024-12-09 | 2024-12-13 |  | OPT Portal Project Week 14 Deliverables.pdf
Rest Password for Email (Password) | Backend Team | P2 | Rajas Telang | Completed | 2024-12-09 | 2024-12-13 | New 16 digit code is needed | OPT Portal Project Week 14 Deliverables.pdf | Next Monday
Rajas is trying JWT tokem thing | Backend Team | P1 | Rajas Telang | Completed | 2024-12-16 | 2024-12-20 |  | OPT Portal Project Week 15 Deliverables.pdf
Gayathri will update 2 people of sure for | Project Manager | P2 | Gayathri Vummenthala | In progress | 2024-12-16 | 2024-12-20 |  | OPT Portal Project Week 15 Deliverables.pdf
Rajas has commented the role based API, Rolwywn needs to merge | Frontend Team | P3 | Rolwyn Quadras | Completed | 2024-12-16 | 2024-12-20 |  | OPT Portal Project Week 15 Deliverables.pdf
User data and roles based authoziation Front end work | Frontend Team | P1 | Rolwyn Quadras | Completed | 2024-12-23 | 2024-12-27 |  | OPT Portal Project Week 16 Deliverables.pdf
Vishrutha , all most done with volunteerning list page, she will share by the end of week | UI/UX Team | P2 | Vishrutha Abbaiah | In progress | 2024-12-23 | 2024-12-27 |  | OPT Portal Project Week 16 Deliverables.pdf
Friday Rajas was working on JWT token | Backend Team | P0 | Rajas Telang | In progress | 2024-12-23 | 2024-12-27 |  | OPT Portal Project Week 16 Deliverables.pdf
Gayathri will share the 2FA password and share on the group | Project Manager | P1 | Gayathri Vummenthala | Completed | 2024-12-23 | 2024-12-27 |  | OPT Portal Project Week 16 Deliverables.pdf
Phase 4 Kickoff and Critical Enhancements | Backend Team | P1 | Rajas Telang | Not started | 2024-12-30 | 2025-01-03 |  | OPT Portal Project Week 17 Deliverables.pdf
Development and Integration | Backend Team | P0 | Rajas Telang | In progress | 2024-12-30 | 2025-01-03 |  | OPT Portal Project Week 17 Deliverables.pdf
Phase 4 Frontend Planning | Frontend Team | P1 | Rolwyn Quadras | Not started | 2024-12-30 | 2025-01-03 |  | OPT Portal Project Week 17 Deliverables.pdf
Component Development and Integration | Frontend Team | P0 | Rolwyn Quadras | In progress | 2024-12-30 | 2025-01-03 |  | OPT Portal Project Week 17 Deliverables.pdf
Phase 4 Design Initiation | UI/UX Team | P1 | Vishrutha Abbaiah | Not started | 2024-12-30 | 2025-01-03 |  | OPT Portal Project Week 17 Deliverables.pdf

## KanbanBoardProject
Task | Team | Priority | Owner | Status | Start date | End date | Milestone | Deliverable | Notes
Kanban and OPT Portal Integration | Backend Team | P0 | Natarajan Pillai | Completed | 2024-10-07 | 2024-10-11 | Integration started | Kanban Board Project Week 9 Deliverable.pdf | Done
Testing and Bug Fixing | Backend Team | P1 | Hitesh Pant | Completed | 2024-10-07 | 2024-10-11 | Resolved the bugs and Images can be added | Kanban Board Project Week 9 Deliverable.pdf | Done
Performance Optimization | Backend Team | P2 | Hitesh Pant | Completed | 2024-10-07 | 2024-10-11 | Team working on it | Kanban Board Project Week 9 Deliverable.pdf | Histesh
Final Testing and Documentation | Backend Team | P3 | Hitesh Pant | Completed | 2024-10-07 | 2024-10-11 | Will move to next week | Kanban Board Project Week 9 Deliverable.pdf
Making Website Dyanamic | Frontend Team | P1 | Manan Gandhi | Completed | 2024-10-07 | 2024-10-11 | Frontend Team still working on the dynamic part | Kanban Board Project Week 9 Deliverable.pdf | DnD functionality is work in progress- 10-12 days required. API for forget password. Connect with Saurav.
People page info; Individual projects; For Login rather than using Jwt token we can use private key or whitelisting ipaddress; And protected routes; Email account | Frontend Team | P0 | Manan Gandhi | Completed | 2024-10-07 | 2024-10-11 | We helped manan with required informations | Kanban Board Project Week 9 Deliverable.pdf | Done
UI Integration for Cross-Project Access | Frontend Team | P1 | Vrushank Hiremath | Completed | 2024-10-07 | 2024-10-11 | Connected both UI/UX team for Integration | Kanban Board Project Week 9 Deliverable.pdf | Done
User Testing and Feedback Collection | Frontend Team | P0 | Vrushank Hiremath | Completed | 2024-10-07 | 2024-10-11 | We took a meeting with Vurshank for some feedback | Kanban Board Project Week 9 Deliverable.pdf | Done
UI/UX Refinement and Bug Fixes | Frontend Team | P0 | Adhyantini Bogawat | Completed | 2024-10-07 | 2024-10-11 | Adhyantini is checking bugs on this | Kanban Board Project Week 9 Deliverable.pdf
Post-Launch Support and Monitoring | Frontend Team | P0 | Adhyantini Bogawat | Blocked | 2024-10-07 | 2024-10-11 | We do it next to next week | Kanban Board Project Week 9 Deliverable.pdf
Unified Design and User Flow | UI/UX Team | P0 | Shrimoyee Banerjee | Completed | 2024-10-07 | 2024-10-11 | Shrimoyee did wireframing | Kanban Board Project Week 9 Deliverable.pdf | Done
Post-launch Usability Testing | UI/UX Team | P0 | Supriya Komarraju | Completed | 2024-10-07 | 2024-10-11 | Supriya did the testing | Kanban Board Project Week 9 Deliverable.pdf | Done
Documentation and Post-launch Support | UI/UX Team | P0 | Shrimoyee Banerjee | Blocked | 2024-10-07 | 2024-10-11 | Will move it to next to next week | Kanban Board Project Week 9 Deliverable.pdf
UI/UX Team Integration | UI/UX Team | P0 | Shrimoyee Banerjee | Completed | 2024-10-07 | 2024-10-11 | Created new Figma file and discussed the flows: From OPT Portal to Kanban Board: Project Tile.; From Kanban Board to OPT; Portal: Profile Page of Volunteer; From Kanban to OPT: People page | Kanban Board Project Week 9 Deliverable.pdf | Done
Implmenting the logic of calendar is bit confusing, Pre existing systems will be easier, We should use Outlook calender API hit limit | Backend Team | P0 | Natarajan Pillai | Completed | 2024-10-14 | 2024-10-18 | Pre existing on will be user. | Kanban Board Project Week 10 Deliverable.pdf | Yes reached out to OPT team and the OPT Team has different backend databases so integrating is difficult. Integrating both databases together it was very difficult.
The OPT Portal and Kanban Board Project should same password and User ID; Hence the database Intregartion should be there. | Backend Team | P1 | Natarajan Pillai | Completed | 2024-10-14 | 2024-10-18 | Need to have a meeting with both Backend teams to resolve this | Kanban Board Project Week 10 Deliverable.pdf | We will connect OPT Portal API with Kanban Board API
Login Page Dynamic | Frontend Team | P0 | Vrushank Hiremath | Completed | 2024-10-14 | 2024-10-18 | Vurshank did the dynamic changes work | Kanban Board Project Week 10 Deliverable.pdf | Done
Admin is Dynamic; PM and Volunteer page will be done by Monday | Frontend Team | P0 | Manan Gandhi | Completed | 2024-10-14 | 2024-10-18 | Manan is working on this will update on Monday regarding same | Kanban Board Project Week 10 Deliverable.pdf
Google calendar API Integration, but a few changes need to be made regarding fetching from a particular calendar | Frontend Team | P1 | Adhyantini Bogawat | Completed | 2024-10-14 | 2024-10-18 | Adhyantini is working on this and get back on Monday | Kanban Board Project Week 10 Deliverable.pdf | Shift accounts
Feature Enhancements and New Integrations | Backend Team | P0 | Natarajan Pillai | Completed | 2024-10-14 | 2024-10-18 | Natrajan did the intergation | Kanban Board Project Week 10 Deliverable.pdf | Done
Monitoring and Error Handling Enhancements | Backend Team | P2 | Hitesh Pant | Completed | 2024-10-14 | 2024-10-18 | Hitesh is debugging few erros | Kanban Board Project Week 10 Deliverable.pdf | Nothing from his end
Planning for Scalability and Upcoming Releases | Backend Team | P2 | Hitesh Pant | Completed | 2024-10-14 | 2024-10-18 | After debugging Hitesh will work on this next week | Kanban Board Project Week 10 Deliverable.pdf
UX Enhancements and New Features | Frontend Team | P1 | Manan Gandhi | Completed | 2024-10-14 | 2024-10-18 | Manan is working on this will update on Monday regarding same | Kanban Board Project Week 10 Deliverable.pdf | Sign Up
Testing and Cross-Browser Compatibility | Frontend Team | P2 | Vrushank Hiremath | Completed | 2024-10-14 | 2024-10-18 | Vrushank will work on this and get back to us by Monday | Kanban Board Project Week 10 Deliverable.pdf | Kanban Board complete
Performance Monitoring and Documentation | Frontend Team | P3 | Adhyantini Bogawat | Completed | 2024-10-14 | 2024-10-18 | Adhyantini will work on this after calender work | Kanban Board Project Week 10 Deliverable.pdf | Calender thing is working
Usability Improvements and New Designs | UI/UX Team | P1 | Supriya Komarraju | Completed | 2024-10-14 | 2024-10-18 | Supriya did the improvement needed for figma design | Kanban Board Project Week 10 Deliverable.pdf | Done
Responsive Design and Error Feedback | UI/UX Team | P2 | Shrimoyee Banerjee | Completed | 2024-10-14 | 2024-10-18 | Shrimoyee is working on this and will update it next week | Kanban Board Project Week 10 Deliverable.pdf | FAQ page is ready and Shirmoyee will share the survey on slack
Outlook calender the reading is possible and no writting is allowed, Gmail able to do both and is done | Frontend Team | P0 | Adhyantini Bogawat | Completed | 2024-10-21 | 2024-10-25 | Adhyantini mentioned the outlook thing will be write function will not be done using northeastern account and google calendar can read and write both the functions | Kanban Board Project Week 11 Deliverable.pdf | Google Calender, Credentials for calender
AWS paid thing beacuse it carshes everytime NPM | Frontend Team | P1 | Manan Gandhi | Completed | 2024-10-21 | 2024-10-25 | Can cost $10-$20, manan will share more information regarding same | Kanban Board Project Week 11 Deliverable.pdf | $49 Budget per month
Final Issue Resolution and Stabilization | Backend Team | P2 | Hitesh Pant | Completed | 2024-10-21 | 2024-10-25 | No issue with AWS | Kanban Board Project Week 11 Deliverable.pdf
System-wide Load and Stress Testing | Backend Team | P3 | Hitesh Pant | Completed | 2024-10-21 | 2024-10-25 | Hitesh did the load testing | Kanban Board Project Week 11 Deliverable.pdf
Phase Two Preparation and Documentation | Backend Team | P2 | Hitesh Pant | Completed | 2024-10-21 | 2024-10-25 | The document is done | Kanban Board Project Week 11 Deliverable.pdf
UI Optimization and Cross-Project Validation | Frontend Team | P1 | Manan Gandhi | Completed | 2024-10-21 | 2024-10-25 | Meeting with manan today, add gayathri | Kanban Board Project Week 11 Deliverable.pdf | Make Dynamic today; Mirror issue will be resolved with Adyantini; Merging was done, Small bug was done. Gmail Access
Performance Monitoring and Final Tweaks | Frontend Team | P2 | Vrushank Hiremath | Completed | 2024-10-21 | 2024-10-25 | Professor $50 maximum per month | Kanban Board Project Week 11 Deliverable.pdf | Login Page is complete; No Sign up page is required beacuse of OPT portal
Frontend Development for Phase Two | Frontend Team | P2 | Vrushank Hiremath | Completed | 2024-10-21 | 2024-10-25 | Vrushnak is completing the rest if phase two requirements | Kanban Board Project Week 11 Deliverable.pdf | Kanban Board Dynamic part is left - 80%
Usability Refinements and Accessibility Validation | UI/UX Team | P3 | Shrimoyee Banerjee | Completed | 2024-10-21 | 2024-10-25 | Meeting with Shrimoyee, add gayathri | Kanban Board Project Week 11 Deliverable.pdf
Usability Testing and Feedback Sessions | UI/UX Team | P2 | Shrimoyee Banerjee | Completed | 2024-10-21 | 2024-10-25 | Shrimoyee created the google form and conducted survey for the same | Kanban Board Project Week 11 Deliverable.pdf
Project manager and admin page live | Frontend Team | P0 | Manan Gandhi | Completed | 2024-10-21 | 2024-10-25 |  | Kanban Board Project Week 12 Deliverable.pdf
Visual Kanban API Development: | Backend Team | P0 | Natarajan Pillai | In progress | 2024-10-28 | 2024-11-01 | Work in Progress | Kanban Board Project Week 12 Deliverable.pdf
Monitoring Setup and Alert Tuning | Backend Team | P1 | Hitesh Pant | In progress | 2024-10-28 | 2024-10-11 |  | Kanban Board Project Week 12 Deliverable.pdf
Security Enhancements | Backend Team | P1 | Hitesh Pant | Not started | 2024-10-28 | 2024-10-11 | Added Action based check, Hitesh will push the code today | Kanban Board Project Week 12 Deliverable.pdf
Phase Two Planning and Documentation: | Backend Team | P3 | Hitesh Pant | Completed | 2024-10-28 | 2024-10-11 | Hitesh completed the documentation and submitted the work | Kanban Board Project Week 12 Deliverable.pdf
Visual Kanban Components Development | Frontend Team | P3 | Manan Gandhi | Not started | 2024-10-28 | 2024-10-11 |  | Kanban Board Project Week 12 Deliverable.pdf
Performance Optimizations | Frontend Team | P0 | Vrushank Hiremath | In progress | 2024-10-28 | 2024-10-11 | Vrushank | Kanban Board Project Week 12 Deliverable.pdf
User Interaction and Error Tracking | Frontend Team | P2 | Adhyantini Bogawat | Completed | 2024-10-28 | 2024-10-11 | Working on FAQ | Kanban Board Project Week 12 Deliverable.pdf
Design Alignment and Phase Two Collaboration | Frontend Team | P2 | Manan Gandhi | Completed | 2024-10-28 | 2024-10-11 |  | Kanban Board Project Week 12 Deliverable.pdf
Kanban Chart Design Finalization | UI/UX Team | P1 | Shrimoyee Banerjee | Completed | 2024-10-28 | 2024-10-11 |  | Kanban Board Project Week 12 Deliverable.pdf
Accessibility Review for New Features | UI/UX Team | P3 | Shrimoyee Banerjee | Completed | 2024-10-28 | 2024-10-11 | Shirmoyee reviewed the work and informed in the meeting | Kanban Board Project Week 12 Deliverable.pdf
Advanced Task Analytics and API Improvements | Backend Team | P2 | Natarajan Pillai | Completed | 2024-11-04 | 2024-11-08 | Work in progress | Kanban Board Project Week 13 Deliverable.pdf
Alerting and Health Monitoring Expansion | Backend Team | P0 | Hitesh Pant | In progress | 2024-11-04 | 2024-11-08 |  | Kanban Board Project Week 13 Deliverable.pdf
API Documentation and Integration | Backend Team | P1 | Hitesh Pant | Completed | 2024-11-04 | 2024-11-08 | Hitesh will update weekly | Kanban Board Project Week 13 Deliverable.pdf
Analytics Dashboard Development | Frontend Team | P3 | Adhyantini Bogawat | Completed | 2024-11-04 | 2024-11-08 | Will work on Next week | Kanban Board Project Week 13 Deliverable.pdf
Error Logging and User Feedback Enhancements | Frontend Team | P2 | Manan Gandhi | In progress | 2024-11-04 | 2024-11-08 |  | Kanban Board Project Week 13 Deliverable.pdf
Performance and Cross-Component Consistency | Frontend Team | P0 | Vrushank Hiremath | Completed | 2024-11-04 | 2024-11-08 |  | Kanban Board Project Week 13 Deliverable.pdf
Analytics Dashboard Design Finalization | UI/UX Team | P1 | Shrimoyee Banerjee | In progress | 2024-11-04 | 2024-11-08 |  | Kanban Board Project Week 13 Deliverable.pdf
Usability Testing and Iterations | UI/UX Team | P2 | Shrimoyee Banerjee | Completed | 2024-11-04 | 2024-11-08 |  | Kanban Board Project Week 13 Deliverable.pdf
Documentation and Component Guidelines | UI/UX Team | P3 | Shrimoyee Banerjee | In progress | 2024-11-04 | 2024-11-08 |  | Kanban Board Project Week 13 Deliverable.pdf
Task Dynamic part | Frontend Team | P0 | Manan Gandhi | Completed | 2024-11-11 | 2024-11-15 |  | Kanban Board Project Week 14 Deliverable.pdf
Full Working software with all functionaliy example adding software | Frontend Team | P1 | Vrushank Hiremath | In progress | 2024-11-11 | 2024-11-15 |  | Kanban Board Project Week 14 Deliverable.pdf
Gmail work | Frontend Team | P0 | Adhyantini Bogawat | Completed | 2024-11-11 | 2024-11-15 |  | Kanban Board Project Week 14 Deliverable.pdf
Monitor System Health and Performance | Backend Team | P0 | Natarajan Pillai | In progress | 2024-11-18 | 2024-11-22 |  | Kanban Board Project Week 15 Deliverable.pdf
Hotfix Deployment | Backend Team | P0 | Hitesh Pant | In progress | 2024-11-18 | 2024-11-22 |  | Kanban Board Project Week 15 Deliverable.pdf
Analyze User Feedback on Backend Performance | Backend Team | P1 | Natarajan Pillai | In progress | 2024-11-18 | 2024-11-22 |  | Kanban Board Project Week 15 Deliverable.pdf
Implement New Requirements from Phase 2 Demo | Backend Team | P1 | Natarajan Pillai | Completed | 2024-11-18 | 2024-11-22 |  | Kanban Board Project Week 15 Deliverable.pdf
Backend Architecture Review | Backend Team | P2 | Hitesh Pant | Completed | 2024-11-18 | 2024-11-22 |  | Kanban Board Project Week 15 Deliverable.pdf
Documentation and Knowledge Transfer | Backend Team | P1 | Natarajan Pillai | Completed | 2024-11-18 | 2024-11-22 |  | Kanban Board Project Week 15 Deliverable.pdf
Monitor User Behavior and Analytics Dashboard Usage | Frontend Team | P0 | Manan Gandhi | In progress | 2024-11-18 | 2024-11-22 |  | Kanban Board Project Week 15 Deliverable.pdf
Quick Bug Fixes and Enhancements | Frontend Team | P0 | Vrushank Hiremath | In progress | 2024-11-18 | 2024-11-22 |  | Kanban Board Project Week 15 Deliverable.pdf
Implement New UI/UX Requirements | Frontend Team | P1 | Adhyantini Bogawat | In progress | 2024-11-18 | 2024-11-22 |  | Kanban Board Project Week 15 Deliverable.pdf
Frontend Optimization | Frontend Team | P1 | Manan Gandhi | In progress | 2024-11-18 | 2024-11-22 |  | Kanban Board Project Week 15 Deliverable.pdf
UI Component Enhancements | Frontend Team | P2 | Vrushank Hiremath | Not started | 2024-11-18 | 2024-11-22 |  | Kanban Board Project Week 15 Deliverable.pdf
Frontend Architecture Review | Frontend Team | P3 | Adhyantini Bogawat | Not started | 2024-11-18 | 2024-11-22 |  | Kanban Board Project Week 15 Deliverable.pdf
Monitor Post-Launch User Interactions | UI/UX Team | P1 | Shrimoyee Banerjee | In progress | 2024-11-18 | 2024-11-22 |  | Kanban Board Project Week 15 Deliverable.pdf
Quick Design Adjustments | UI/UX Team | P0 | Shrimoyee Banerjee | Not started | 2024-11-18 | 2024-11-22 |  | Kanban Board Project Week 15 Deliverable.pdf
Usability Testing for New Concepts | UI/UX Team | P0 | Shrimoyee Banerjee | Not started | 2024-11-18 | 2024-11-22 |  | Kanban Board Project Week 15 Deliverable.pdf
Wireframing and Design Specifications | UI/UX Team | P1 | Shrimoyee Banerjee | In progress | 2024-11-18 | 2024-11-22 |  | Kanban Board Project Week 15 Deliverable.pdf
Update Style Guides and Design Systems | UI/UX Team | P2 | Shrimoyee Banerjee | In progress | 2024-11-18 | 2024-11-22 |  | Kanban Board Project Week 15 Deliverable.pdf
Project Seach functionality | Frontend Team | P0 | Natarajan Pillai | In progress | 2024-11-18 | 2024-11-22 | Natarajan will connect with Hitesh and update Manan | Kanban Board Project Week 15 Deliverable.pdf
Updated all Projects Details in Kanban Database | Frontend Team | P1 | Vrushank Hiremath | Completed | 2024-11-18 | 2024-11-22 | Gayathri will update us | Kanban Board Project Week 15 Deliverable.pdf | By the end of this week
Kanban Board Drag and Drop Functionality | Frontend Team | P1 | Vrushank Hiremath | Completed | 2024-11-18 | 2024-11-22 | Vrushank has completed the task | Kanban Board Project Week 15 Deliverable.pdf
Manan will push code on server | Frontend Team | P2 | Manan Gandhi | In progress | 2024-11-19 | 2024-11-22 | Will do it after call | Kanban Board Project Week 15 Deliverable.pdf
People's Page(Is Static now) | Frontend Team | P2 | Adhyantini Bogawat | In progress | 2024-11-20 | 2024-11-22 |  | Kanban Board Project Week 15 Deliverable.pdf | s
Admin Page needs to be change. | UI/UX Team | P0 | Shrimoyee Banerjee | In progress | 2024-11-21 | 2024-11-22 | API changes | Kanban Board Project Week 15 Deliverable.pdf | Not yet
API Documents of OPT portal. | Frontend Team | P1 | Manan Gandhi | Completed | 2024-11-22 | 2024-11-22 | Manan needed to be connected with Rajas | Kanban Board Project Week 15 Deliverable.pdf
Search functionality | Backend Team | P1 | Hitesh Pant | In progress | 2024-11-25 | 2024-11-29 |  | Kanban Board Project Week 16 Deliverable.pdf
Advanced Analytics API Development | Backend Team | P0 | Hitesh Pant | In progress | 2024-11-25 | 2024-11-29 |  | Kanban Board Project Week 16 Deliverable.pdf
System Performance Optimization | Backend Team | P1 | Hitesh Pant | Completed | 2024-11-25 | 2024-11-29 |  | Kanban Board Project Week 16 Deliverable.pdf
Backend Code Review and Phase Three Sync-Up | Backend Team | P1 | Hitesh Pant | In progress | 2024-11-25 | 2024-11-29 |  | Kanban Board Project Week 16 Deliverable.pdf
CEO Dashboard Enhancements | Frontend Team | P2 | Manan Gandhi | Completed | 2024-11-25 | 2024-11-29 |  | Kanban Board Project Week 16 Deliverable.pdf
Develop Reporting Widgets | Frontend Team | P2 | Vrushank Hiremath | In progress | 2024-11-25 | 2024-11-29 |  | Kanban Board Project Week 16 Deliverable.pdf
Enhance Filters and Sorting | Frontend Team | P1 | Adhyantini Bogawat | In progress | 2024-11-25 | 2024-11-29 |  | Kanban Board Project Week 16 Deliverable.pdf
Admin Page and Feature Expansion | Frontend Team | P2 | Manan Gandhi | In progress | 2024-11-25 | 2024-11-29 |  | Kanban Board Project Week 16 Deliverable.pdf
Collaborative Planning for Upcoming Features | Frontend Team | P2 | Adhyantini Bogawat | In progress | 2024-11-25 | 2024-11-29 |  | Kanban Board Project Week 16 Deliverable.pdf
CEO Dashboard Design Finalization | UI/UX Team | P1 | Shrimoyee Banerjee | Blocked | 2024-11-25 | 2024-11-29 |  | Kanban Board Project Week 16 Deliverable.pdf
Admin Page and Wireframing | UI/UX Team | P2 | Shrimoyee Banerjee | Blocked | 2024-11-25 | 2024-11-29 |  | Kanban Board Project Week 16 Deliverable.pdf
Documentation and Alignment | UI/UX Team | P3 | Shrimoyee Banerjee | In progress | 2024-11-25 | 2024-11-29 |  | Kanban Board Project Week 16 Deliverable.pdf
API Development and Optimization | Backend Team | P1 | Hitesh Pant | In progress | 2024-12-02 | 2024-12-06 |  | Kanban Board Project Week 17 Deliverables.pdf
Database and Caching Enhancements | Backend Team | P1 | Hitesh Pant | In progress | 2024-12-02 | 2024-12-06 |  | Kanban Board Project Week 17 Deliverables.pdf
Security and Validation | Backend Team | P2 | Hitesh Pant | In progress | 2024-12-02 | 2024-12-06 |  | Kanban Board Project Week 17 Deliverables.pdf
Feature Integration Testing | Backend Team | P2 | Hitesh Pant | In progress | 2024-12-02 | 2024-12-06 |  | Kanban Board Project Week 17 Deliverables.pdf
Documentation and Handoff | Backend Team | P2 | Hitesh Pant | In progress | 2024-12-02 | 2024-12-06 |  | Kanban Board Project Week 17 Deliverables.pdf
UI Development for Software Tour | Frontend Team | P2 | Manan Gandhi | Completed | 2024-12-02 | 2024-12-06 |  | Kanban Board Project Week 17 Deliverables.pdf
Enhanced Role Management UI | Frontend Team | P3 | Vrushank Hiremath | Completed | 2024-12-02 | 2024-12-06 |  | Kanban Board Project Week 17 Deliverables.pdf
Performance Optimization | Frontend Team | P1 | Adhyantini Bogawat | In progress | 2024-12-02 | 2024-12-06 |  | Kanban Board Project Week 17 Deliverables.pdf
Testing and Bug Fixes | Frontend Team | P2 | Manan Gandhi | In progress | 2024-12-02 | 2024-12-06 |  | Kanban Board Project Week 17 Deliverables.pdf
Documentation and Planning | Frontend Team | P3 | Adhyantini Bogawat | In progress | 2024-12-02 | 2024-12-06 |  | Kanban Board Project Week 17 Deliverables.pdf
Finalize Onboarding Designs | UI/UX Team | P1 | Shrimoyee Banerjee | In progress | 2024-12-02 | 2024-12-06 |  | Kanban Board Project Week 17 Deliverables.pdf
Design Testing | UI/UX Team | P2 | Shrimoyee Banerjee | In progress | 2024-12-02 | 2024-12-06 |  | Kanban Board Project Week 17 Deliverables.pdf
Visual Asset Creation | UI/UX Team | P2 | Shrimoyee Banerjee | Not started | 2024-12-02 | 2024-12-06 |  | Kanban Board Project Week 17 Deliverables.pdf
Retrospective and Ideation | UI/UX Team | P0 | Shrimoyee Banerjee | Not started | 2024-12-02 | 2024-12-06 |  | Kanban Board Project Week 17 Deliverables.pdf
Search functionality | Backend Team | P2 | Hitesh Pant | Completed | 2024-12-09 | 2024-12-13 | Backend work is done | Kanban Board Project Week 17 Deliverables.pdf
Final Refinements and Bug Fixes | Backend Team | P0 | Hitesh Pant | Completed | 2024-12-09 | 2024-12-13 |  | Kanban Board Project Week 18 Deliverables.pdf
Comprehensive Backend Testing | Backend Team | P1 | Hitesh Pant | In progress | 2024-12-09 | 2024-12-13 |  | Kanban Board Project Week 18 Deliverables.pdf
Documentation and Deployment Preparation | Backend Team | P0 | Hitesh Pant | In progress | 2024-12-09 | 2024-12-13 | Work is in progress | Kanban Board Project Week 18 Deliverables.pdf
Feature Polishing and QA | Frontend Team | P1 | Adhyantini Bogawat | Completed | 2024-12-09 | 2024-12-13 |  | Kanban Board Project Week 18 Deliverables.pdf
Comprehensive Testing and Bug Fixes | Frontend Team | P2 | Adhyantini Bogawat | In progress | 2024-12-09 | 2024-12-13 |  | Kanban Board Project Week 18 Deliverables.pdf
Usability Testing and Handoff | Frontend Team | P3 | Adhyantini Bogawat | In progress | 2024-12-09 | 2024-12-13 |  | Kanban Board Project Week 18 Deliverables.pdf
Frontend Gmail | Frontend Team | P3 | Adhyantini Bogawat | Completed | 2024-12-09 | 2024-12-13 | Work in progress | Kanban Board Project Week 18 Deliverables.pdf
Ujwal will working with Hitesh on role based authorization | Backend Team | P1 | Ujwal Gupta | Completed | 2024-12-16 | 2024-12-20 | Work in Progress | Kanban Board Project Week 19 Deliverables.pdf
Adhyanti will be pushing the code today | Backend Team | P2 | Adhyantini Bogawat | Completed | 2024-12-16 | 2024-12-20 | Adhayantini | Kanban Board Project Week 19 Deliverables.pdf
Titiksha will start deploying the code for phase 2 | Cloud Team | P1 | Titiksha Ghosh | In progress | 2024-12-16 | 2024-12-20 | Titiksha has logged into AWS and Will start work from Monday | Kanban Board Project Week 19 Deliverables.pdf
Hitesh was travelling back to US hence he was absent | Backend Team | P1 | Hitesh Pant | Completed | 2024-12-16 | 2024-12-20 | We working bug on additional code. | Kanban Board Project Week 19 Deliverables.pdf
Gayathri will be helping us with one Frontend engineer and one Ui/Ux engineer | Project Manager | P0 | Gayathri Vummenthala | In progress | 2024-12-16 | 2024-12-20 | Gayathri will talk to 3- 4 people | Kanban Board Project Week 19 Deliverables.pdf
Bug fix that histesh and ujwal are working is fixed | Backend Team | P0 | Ujwal Gupta | In progress | 2024-12-23 | 2024-12-27 |  | Kanban Board Project Week 20 Deliverables.pdf
Api testing for other service, created a task and team group | Backend Team | P1 | Ujwal Gupta | In progress | 2024-12-23 | 2024-12-27 |  | Kanban Board Project Week 20 Deliverables.pdf
Same update from Titiksha and she was able to login. | Cloud Team | P2 | Titiksha Ghosh | In progress | 2024-12-23 | 2024-12-27 | The cost thing titksha will update by end of week | Kanban Board Project Week 20 Deliverables.pdf
Stabilization and Final Fixes | Backend Team | P1 | Hitesh Pant | Not started | 2024-12-30 | 2025-01-03 |  | Kanban Board Project Week 21 Deliverables.pdf
Documentation and Handoff | Backend Team | P2 | Hitesh Pant | In progress | 2024-12-30 | 2025-01-03 |  | Kanban Board Project Week 21 Deliverables.pdf
Final UI Fixes and Enhancements | Frontend Team | P1 | Adhyantini Bogawat | Not started | 2024-12-30 | 2025-01-03 |  | Kanban Board Project Week 21 Deliverables.pdf
Documentation and Support Handoff | Frontend Team | P0 | Adhyantini Bogawat | In progress | 2024-12-30 | 2025-01-03 |  | Kanban Board Project Week 21 Deliverables.pdf
Final Design Refinements | UI/UX Team | P1 | Gayathri Vummenthala | Not started | 2024-12-30 | 2025-01-03 | No resource | Kanban Board Project Week 21 Deliverables.pdf
Documentation and Design Handoff | UI/UX Team | P3 | Gayathri Vummenthala | Not started | 2024-12-30 | 2025-01-03 |  | Kanban Board Project Week 21 Deliverables.pdf