## Slide 1: Kanban Board for OPT Portal
Project Proposal

## Slide 2: Project Overview
Implementation of a Kanban Board to centralize volunteer management and Project Management for Bear Brown and Co and Abecedarian LLC.
Key Benefits:
Centralized Project Management
Enhanced Organization
Efficient Volunteer Assignment
Regular Project Updates.

## Slide 3: Project Scope
In-Scope:
Assigning volunteers to specific tasks
Software selection and configuration
User roles and permissions setup
Project and task management
Out-of-Scope:
1. Integration with the OPT portal
2. Ongoing project management after setup

## Slide 4: Deliverables
Fully Functional and configured Kanban Board
User accounts and Roles Assigned
Initial Projects and tasks entered into the system
Regular updates and reporting mechanism

## Slide 5: Constraints and Risks
Constraints
Completion timeline: 6 weeks
2. Risks
Potential team changes
Technical issues during testing
Possible project delays

## Slide 6: Project Timeline
Week 1-2: Team Selection, Software and language selection, initial setup
Week 3-4: User account creation, role assignments, initial project entry
Week 5-6: Training, testing, and deployment

## Slide 7: Team Structure
Project Manager: Gayathri Vummenthala – Oversees development and manages timelines
Product Manager: Rahul Ashok Kodate – Defines requirements and ensures software meets business objectives
UI/UX Designer: Shrimoyee Banerjee, - Designs user-friendly interface
Frontend Developer: [Names] – Implements design and builds UI
Backend Developer: [Names] – Manages server-side logic database

## Slide 8: Requirements and Overview
Functional Requirements:
User roles and Permissions
Kanban Board features
Reporting and analytics
Integration (Calendar, APT access)
Non-Functional Requirements:
Performance, Security, usability and reliability
Compatibility with major browsers and devices

## Slide 9: Technical Details
Technology Stack:
Frontend:
Backend:
Database:
UI/UX: Figma
Hosting:
Development Environment:
CI/CD Pipeline, testing frameworks, Development tools

## Slide 10: Support and Maintenance
Set up support and issue reporting systems
Define maintenance plans for regular updates and debugging

## Slide 11: Project Plan
Design: UI/UX creation, software architecture planning
Develop: Frontend and backend development, API integration
Testing: Unit, integration, user testing
Deployment: Staging and production environment deployment

## Slide 12: Conclusions
Next steps:
Forming a team of amazing developers
Gathering all the information regarding multiple projects
Developing a maintenance plan